## mplad_projects
project_id | project_name | state | district | constituency | category | sanctioned_amount | estimated_cost | actual_expenditure | amount_released | amount_utilized | start_date | expected_completion_date | actual_completion_date | vendor | status
MPLAD001 | Government School Renovation | Telangana | Hyderabad | HYD001 | Education | 1000000 | 950000 | 920000 | 950000 | 920000 | 2025-01-10 | 2025-04-10 | 2025-04-05 | ABC Constructions | Completed
MPLAD002 | Rural Road Development | Telangana | Warangal | WGL001 | Roads | 1500000 | 1450000 | 1480000 | 1450000 | 1480000 | 2025-02-01 | 2025-06-01 | 2025-06-10 | XYZ Infra | Completed
MPLAD003 | Community Health Center | Andhra Pradesh | Guntur | GNT001 | Health | 2000000 | 1950000 | 1980000 | 1950000 | 1980000 | 2025-01-15 | 2025-07-15 | 2025-07-20 | HealthBuild Pvt Ltd | Completed
MPLAD004 | Street Lighting Project | Karnataka | Bengaluru | BLR001 | Infrastructure | 800000 | 780000 | 790000 | 780000 | 790000 | 2025-03-01 | 2025-05-01 | 2025-05-05 | LightTech | Completed
MPLAD005 | Drinking Water Facility | Telangana | Nalgonda | NLG001 | Water | 1200000 | 1150000 | 1160000 | 1150000 | 1160000 | 2025-02-10 | 2025-06-10 | 2025-06-15 | WaterWorks | Completed
MPLAD006 | School Computer Lab | Kerala | Kochi | KOC001 | Education | 900000 | 880000 | 870000 | 880000 | 870000 | 2025-01-20 | 2025-04-20 | 2025-04-18 | TechBuild | Completed
MPLAD007 | Village Road Repair | Maharashtra | Pune | PUN001 | Roads | 1300000 | 1250000 | 1280000 | 1250000 | 1280000 | 2025-02-05 | 2025-06-05 | 2025-06-08 | Metro Infra | Completed
MPLAD008 | Primary Health Center Upgrade | Tamil Nadu | Madurai | MDU001 | Health | 1800000 | 1750000 | 1780000 | 1750000 | 1780000 | 2025-01-05 | 2025-07-05 | 2025-07-10 | MedBuild | Completed
MPLAD009 | Public Library Construction | Telangana | Karimnagar | KMN001 | Education | 1100000 | 1080000 | 1070000 | 1080000 | 1070000 | 2025-03-05 | 2025-08-05 | 2025-08-02 | ABC Constructions | Completed
MPLAD010 | Drainage Improvement | Andhra Pradesh | Vijayawada | VJA001 | Infrastructure | 1400000 | 1350000 | 1390000 | 1350000 | 1390000 | 2025-02-15 | 2025-06-15 | 2025-06-20 | UrbanWorks | Completed
MPLAD011 | Road Widening Project | Telangana | Hyderabad | HYD002 | Roads | 1200000 | 1150000 | 2900000 | 1150000 | 900000 | 2025-01-10 | 2025-05-10 | 2025-11-30 | XYZ Infra | Delayed
MPLAD012 | School Building Extension | Andhra Pradesh | Guntur | GNT002 | Education | 1600000 | 1550000 | 3200000 | 1550000 | 1100000 | 2025-02-01 | 2025-07-01 | 2025-12-20 | XYZ Infra | Delayed
MPLAD013 | Water Pipeline Project | Karnataka | Mysuru | MYS001 | Water | 1000000 | 980000 | 1010000 | 980000 | 120000 | 2025-03-01 | 2025-06-01 |  | WaterWorks | Ongoing
MPLAD014 | Community Hall Construction | Telangana | Warangal | WGL002 | Infrastructure | 900000 | 850000 | 2100000 | 850000 | 800000 | 2025-01-15 | 2025-05-15 | 2025-10-30 | ABC Constructions | Delayed
MPLAD015 | Rural Health Center | Kerala | Kochi | KOC002 | Health | 1700000 | 1650000 | 1750000 | 1650000 | 300000 | 2025-02-10 | 2025-08-10 |  | MedBuild | Ongoing
MPLAD016 | Street Road Repair | Maharashtra | Pune | PUN002 | Roads | 1000000 | 950000 | 1020000 | 950000 | 950000 | 2025-03-10 | 2025-06-10 | 2025-06-12 | Metro Infra | Completed
MPLAD017 | School Furniture Supply | Tamil Nadu | Madurai | MDU002 | Education | 700000 | 680000 | 690000 | 680000 | 690000 | 2025-02-20 | 2025-04-20 | 2025-04-22 | TechBuild | Completed
MPLAD018 | Drainage Construction | Telangana | Nalgonda | NLG002 | Infrastructure | 1250000 | 1200000 | 1270000 | 1200000 | 1270000 | 2025-01-25 | 2025-06-25 | 2025-06-28 | UrbanWorks | Completed
MPLAD019 | Water Tank Construction | Andhra Pradesh | Vijayawada | VJA002 | Water | 1000000 | 980000 | 980000 | 980000 | 980000 | 2025-03-01 | 2025-07-01 | 2025-07-05 | WaterWorks | Completed
MPLAD020 | Government School Repair | Telangana | Karimnagar | KMN002 | Education | 950000 | 900000 | 920000 | 900000 | 920000 | 2025-02-01 | 2025-05-01 | 2025-05-04 | ABC Constructions | Completed